

International School

Capstone Project 2

CMU-SE 451

**Sprint Backlog**

**Version 2.5**

**Date: 18/05/2021**

**ViVu - The smart travel system supports with chatbot and short video social network**

**Submitted by**

**Sang, Nguyen Thanh**

**Thuyen, Pham Van**

**Tuan, Doan Kim**

**Loc, Phung Hoang Phu**

**Approved by Nguyen Duc Man**

**Review Panel Representative:**

Name Signature Date

**Capstone Project 2- Mentor:**

Name Signature Date

# **Project Information**

|  |  |  |  |
| --- | --- | --- | --- |
| **Project acronym** | ViVu | | |
| **Project Title** | The smart travel system supports chatbot and integrates short video social network | | |
| **Start Date** | 22 Feb 2021 | **End Date** | 30 May 2021 |
| **Lead Institution** | International School, Duy Tan University | | |
| **Project Mentor** | Man, Nguyen Duc, Ph.D | | |
| **Scrum master**  **/ Project Leader & contact details** | Sang, Nguyen Thanh  Ema[il: thanhsang3111999.ntb@gmail.com](mailto:thanhsang3111999.ntb@gmail.com)  Tel: 0344684069  ID: 23211212363 | | |
| **Partner Organization** |  | | |
| **Project Web URL** |  | | |
| **Team members** | Name | Email | Tel |
| 2321121321 | Tuan, Doan Kim | [doantuan21101999@gmail.com](mailto:doantuan21101999@gmail.com) | 0913622928 |
| 2321124963 | Loc, Phung Hoang Phu | [phunghoangphuloc@gmail.com](mailto:phunghoangphuloc@gmail.com) | 0912698173 |
| 2321125061 | Thuyen, Pham Van | [phamvanthuyen2802@gmail.com](mailto:phamvanthuyen2802@gmail.com) | 0795697332 |

# **Sprint Backlog Document**

|  |  |  |  |
| --- | --- | --- | --- |
| **Document Title** | Sprint Backlog Document |  |  |
| **Reporting Period** |  |  |  |
| **Author(s) & Project** | Sang, Nguyen Thanh, Scrum Master | |  |
| **Team Information** | **Name** | **Role** |  |
| Sang, Nguyen Thanh | Member |  |
| Tuan, Doan Kim | Member |  |
| Thuyen, Pham Van | Member |  |
| Loc, Phung Hoang Phu | Member |  |
| **Date** | 18/05/2021 | **Filename** | Sprint\_Backlog\_V2.5.docx |
| **Access** | Project and CMU Program | |  |

|  |  |  |
| --- | --- | --- |
| Document History | | |
| **Version** | **Date** | **Comments** |
| V2.0 | 08/03/2021 | Create Sprint Backlog Sprint 1 |
| V2.1 | 22/03/2021 | Update Sprint Backlog Sprint 2 |
| V2.2 | 05/04/2021 | Update Sprint Backlog Sprint 3 |
| V2.3 | 19/04/2021 | Update Sprint Backlog Sprint 4 |
| V2.4 | 03/05/2021 | Update Sprint Backlog Sprint 5 |
| V2.5 | 18/05/2021 | Update Sprint Backlog Sprint 6 |

# **Document Approvals**

The following signatures are required for approval of this document.

|  |  |  |
| --- | --- | --- |
| MSc Man, Nguyen Duc  Mentor |  | Date |
| Sang, Nguyen Thanh  Scrum master, Dev |  | Date |
| Tuan, Doan Kim   Product Owner, Dev |  | Date |
| Thuyen, Pham Van   Dev, Tester |  | Date |
| Loc, Phung Hoang Phu   Dev |  | Date |

**TABLE OF CONTENTS**

[**Project Information** 1](#_Toc72953198)

[**Sprint Backlog Document** 2](#_Toc72953199)

[**Document Approvals** 3](#_Toc72953200)

[**1.** **Sprint 1** 5](#_Toc72953201)

[**2.** **Sprint 2** 11](#_Toc72953202)

[**3.** **Sprint 3** 17](#_Toc72953203)

[**4.** **Sprint 4** 23](#_Toc72953204)

[**5.** **Sprint 5** 29](#_Toc72953205)

[**6.** **Sprint 6** 35](#_Toc72953206)

1. **Sprint 1**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Task | Responsible person | Status | Estimate (hours) | Start Date | End Date |
|  | Sprint kickoff meeting | All members | done | 4 | 08/03 | 08/03 |
|  | Collect all requirements of Travel system | All members | done | 15 | 08/03 | 10/03 |
|  | Collect all requirements of Short Video Social Network | All members | done | 16 | 09/03 | 12/03 |
|  | Analyze all requirements | All members | done | 14 | 13/03 | 16/03 |
|  | Update Database Design Document | Loc Phung | done | 5 | 15/03 | 15/03 |
|  | Update Architecture Design Document | Sang Nguyen | done | 10 | 17/03 | 18/03 |
|  | Update Product Backlog | Tuan Doan | done | 6 | 16/03 | 17/03 |
|  | Update User Story | Thuyen Pham | done | 8 | 19/03 | 20/03 |
|  | Update Interface Design Document | Tuan Doan | done | 5 | 18/03 | 19/03 |
|  | Create Test Plan for Sprint 1 | Thuyen Pham | done | 4 | 09/03 | 10/03 |
|  | Design Testcase for Sprint 1 | Thuyen Pham | done | 8 | 11/03 | 13/03 |
|  | Add social network screen | Sang Nguyen | done | 12 | 18/03 | 20/03 |
|  | Add post, user\_following, interacting\_post, comment tables in database | Loc Phung | done | 5 | 19/03 | 21/03 |
|  | Change UI for app | Tuan Doan | done | 9 | 20/03 | 21/03 |
|  | Re-develop UI for list tours | Sang Nguyen | done | 7 | 19/03 | 20/03 |
|  | Test for Sprint 1 | Thuyen Pham | done | 10 | 20/03 | 21/03 |
|  | Team Daily meeting | All members | done | 10 | 08/03 | 20/03 |
|  | Sprint Review meeting | All members | done | 8 | 13/03 | 13/03 |
|  | Sprint Retrospective | All members | done | 4 | 21/03 | 21/03 |
|  |  |  |  | 160 | 08/03 | 21/03 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone | 07/  03 | 08/  03 | 09/ 03 | 10/  03 | 11/  09 | 12/  03 | 13/  03 | 14/  03 | 15/  03 | 16/  03 | 17/  03 | 18/  03 | 19/  03 | 20/  03 | 21/  03 |
| Estimated Time (Hours) | 160 | 148.6 | 137.1 | 125.7 | 114.3 | 102.9 | 91.4 | 80 | 68.6 | 57.1 | 45.7 | 34.3 | 22.9 | 11.4 | 0 |
| Actual Time Remaining(Hours) | 160 | 156 | 155 | 152 | 150 | 120 | 97 | 97 | 95 | 73 | 61 | 42 | 20 | 8 | 0 |
| Actual Time(Hours) | 0 | 4 | 1 | 3 | 2 | 30 | 23 | 0 | 2 | 22 | 12 | 19 | 22 | 12 | 8 |
| Sprint kickoff meeting | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Collect all requirements of Travel system | 0 | 0 | 1 | 2 | 1 | 5 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |
| Collect all requirements of Short Video Social Network | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 |
| Analyse all requirements | 0 | 0 | 0 | 0 | 1 | 4 | 3 | 0 | 0 | 4 | 0 | 2 | 0 | 0 | 0 |
| Update Database Design Document | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Architecture Design Document | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 |
| Update Product Backlog | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 |
| Update User Story | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 |
| Update Interface Design Document | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 |
| Create Test Plan for Sprint 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 |
| Design Testcase for Sprint 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 |
| Add social network screen | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 5 | 2 | 0 |
| Add post, user\_following, interacting\_post, comment tables in database | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 |
| Change UI for app | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 2 | 0 |
| Re-develop UI for list tours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 1 |
| Test for Sprint 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 4 | 0 |
| Team Daily meeting | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 2 | 0 |
| Sprint Review meeting | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Sprint Retrospective | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |

1. **Sprint 2**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Task | Responsible person | Status | Estimate (hours) | Start Date | End Date |
|  | Sprint kickoff meeting | All members | done | 4 | 22/03 | 22/03 |
|  | Update Product Backlog | Tuan Doan | done | 2 | 22/03 | 23/03 |
|  | Update User Story | All members | done | 2 | 22/03 | 24/03 |
|  | Update Sprint Backlog | Sang Nguyen | done | 5 | 23/03 | 24/03 |
|  | Update Architecture Design Document | Sang Nguyen | done | 3 | 25/03 | 26/03 |
|  | Update Interface Design Document | Tuan Doan | done | 4 | 24/03 | 27/03 |
|  | Create Test Plan for Sprint 2 | Thuyen Pham | done | 3 | 25/03 | 25/03 |
|  | Design Test Case for Sprint 2 | Thuyen Pham | done | 8 | 26/03 | 28/03 |
|  | Re-develop UI for tour detail | Tuan Doan | done | 5 | 26/03 | 27/03 |
|  | Handle UI for creating tour schedule on chatbot | Sang Nguyen | done | 12 | 25/03 | 28/03 |
|  | Integrate shortest path algorithm for efficient schedule generation | Sang Nguyen | done | 6 | 27/03 | 29/03 |
|  | Research Video Content Detection | Thuyen Pham | done | 18 | 27/03 | 30/03 |
|  | Develop UI for social network in main screen | Loc Phung | done | 6 | 28/03 | 30/03 |
|  | Create API for get list post | Loc Phung | done | 3 | 29/03 | 31/03 |
|  | Create API for list trending post | Sang Nguyen | done | 5 | 30/03 | 31/03 |
|  | Develop scan ticket feature | Thuyen Pham | not done | 8 | 01/04 | 03/04 |
|  | Integrate map checking places | Tuan Doan | not done | 9 | 01/04 | 03/04 |
|  | Apply voucher in app | Tuan Doan | done | 6 | 02/04 | 03/04 |
|  | Create API for getting list voucher | Loc Phung | done | 6 | 01/04 | 02/04 |
|  | Handle applying voucher for user | Thuyen Pham | done | 3 | 03/04 | 03/04 |
|  | Test for Sprint 2 | Thuyen | done | 20 | 01/04 | 04/04 |
|  | Team Daily meeting | All members | done | 14 | 22/03 | 03/04 |
|  | Sprint Review meeting | All members | done | 4 | 27/03 | 27/03 |
|  | Sprint Retrospective | All members | done | 4 | 04/04 | 04/04 |
|  |  |  |  | 160 | 22/03 | 04/04 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone | 21/  03 | 22/ 03 | 23/  03 | 24/  03 | 25/  03 | 26/  03 | 27/  03 | 28/  03 | 29/  03 | 30/  03 | 31/  03 | 01/  04 | 02/  04 | 03/  04 | 04/  04 |
| Estimated Time (Hours) | 160 | 148.6 | 137.1 | 125.7 | 114.3 | 102.9 | 91.4 | 80 | 68.6 | 57.1 | 45.7 | 34.3 | 22.9 | 11.4 | 0 |
| Actual Time Remaining(Hours) | 160 | 154 | 150 | 143 | 123 | 119 | 98 | 83 | 80 | 76 | 70 | 65 | 43 | 28 | 16 |
| Actual Time(Hours) | 0 | 6 | 4 | 7 | 20 | 4 | 21 | 15 | 3 | 4 | 6 | 5 | 22 | 15 | 12 |
| Sprint kickoff meeting | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Product Backlog | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update User Story | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Sprint Backlog | 0 | 1 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Architecture Design Document | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Interface Design Document | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Create Test Plan for Sprint 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Design Test Case for Sprint 2 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Re-develop UI for tour detail | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Handle UI for creating tour schedule on chatbot | 0 | 0 | 0 | 0 | 4 | 1 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Integrate shortest path algorithm for efficient schedule generation | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Research Video Content Detection | 0 | 0 | 0 | 0 | 4 | 2 | 3 | 3 | 0 | 0 | 0 | 2 | 4 | 0 | 0 |
| Develop UI for social network in main screen | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 1 | 0 | 0 | 0 |
| Create API for get list post | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 |
| Create API for list trending post | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 |
| Develop scan ticket feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Integrate map checking places | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |
| Apply voucher in app | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 3 | 0 | 0 |
| Create API for getting list voucher | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |
| Handle applying voucher for user | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |
| Test for Sprint 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 5 | 6 | 6 |
| Team Daily meeting | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 2 | 2 | 2 |
| Sprint Review meeting | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Sprint Retrospective | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |

1. **Sprint 3**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Task | Responsible person | Status | Estimate (hours) | Start Date | End Date |
|  | Sprint kickoff meeting | All members | done | 4 | 05/04 | 05/04 |
|  | Update Sprint Backlog | Sang Nguyen | done | 6 | 05/04 | 06/04 |
|  | Update Architecture Design Document | Tuan Doan | done | 4 | 06/04 | 08/04 |
|  | Update Test Plan | Thuyen Pham | done | 4 | 06/04 | 07/04 |
|  | Design Test Case for Sprint 3 | Thuyen Pham | done | 6 | 08/04 | 10/04 |
|  | Develop scan ticket feature | Sang Nguyen | not done | 8 | 07/04 | 09/04 |
|  | Integrate map checking places | Tuan Doan | done | 10 | 07/04 | 10/04 |
|  | Integrate advertisements in app | Loc Phung | not done | 10 | 09/04 | 12/04 |
|  | Develop UI for post video in social network | Sang Nguyen | done | 7 | 08/04 | 13/04 |
|  | Upload video to google storage | Loc Phung | done | 9 | 11/04 | 13/04 |
|  | Create API for posting video | Sang Nguyen | done | 11 | 12/04 | 14/04 |
|  | Enhance UI in post to interact emotion in videos | Thuyen Pham | done | 7 | 11/04 | 14/04 |
|  | Develop API for like and dislike a post | Tuan Doan | done | 6 | 13/04 | 15/04 |
|  | Enhance UI to comment in a post | Tuan Doan | done | 8 | 14/04 | 16/04 |
|  | Develop API for commenting a post | Sang Nguyen | done | 7 | 15/04 | 16/04 |
|  | Create UI for user seft-manage social network videos | Sang Nguyen | done | 11 | 15/04 | 17/04 |
|  | Develop API for getting list post by user ID | Loc Phung | done | 9 | 15/04 | 16/04 |
|  | Test for Sprint 3 | Thuyen Pham | done | 21 | 10/04 | 18/04 |
|  | Team Daily meeting | All members | done | 16 | 05/04 | 17/04 |
|  | Sprint Review meeting | All members | done | 8 | 09/04 | 09/04 |
|  | Sprint Retrospective | All members | done | 4 | 18/04 | 18/04 |
|  |  |  |  | 176 | 05/04 | 18/04 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone | 04/  04 | 05/ 04 | 06/  04 | 07/ 04 | 08/  04 | 09/ 04 | 04/  04 | 11/  04 | 12/ 04 | 13/  04 | 14/  04 | 15/  04 | 16/  04 | 17/  04 | 18/  04 |
| Estimated Time (Hours) | 176 | 163.4 | 150.9 | 138.3 | 125.7 | 113.1 | 100.6 | 88 | 75.4 | 62.9 | 50.3 | 37.7 | 25.1 | 12.6 | 0 |
| Actual Time Remaining(Hours) | 176 | 160 | 145 | 140 | 136 | 130 | 100 | 92 | 87 | 86 | 71 | 54 | 52 | 38 | 17 |
| Actual Time(Hours) | 0 | 16 | 15 | 5 | 4 | 6 | 30 | 8 | 5 | 1 | 15 | 17 | 2 | 14 | 21 |
| Sprint kickoff meeting | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Sprint Backlog | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Architecture Design Document | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Test Plan | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Design Test Case for Sprint 3 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Develop scan ticket feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |
| Integrate map checking places | 0 | 1 | 2 | 2 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Integrate advertisements in app | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Develop UI for post video in social network | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Upload video to google storage | 0 | 0 | 0 | 0 | 1 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Create API for posting video | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 2 | 0 | 2 | 0 | 0 | 0 | 0 |
| Enhance UI in post to interact emotion in videos | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |
| Develop API for like and dislike a post | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 |
| Enhance UI to comment in a post | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 4 |
| Develop API for commenting a post | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 1 | 1 |
| Create UI for user seft-manage social network videos | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 3 | 0 | 1 | 3 |
| Develop API for getting list post by user ID | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 2 |
| Test for Sprint 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 5 | 1 | 5 | 6 |
| Team Daily meeting | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 2 | 1 | 0 | 3 | 3 | 0 | 2 | 0 |
| Sprint Review meeting | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Sprint Retrospective | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |

1. **Sprint 4**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Task | Responsible person | Status | Estimate (hours) | Start Date | End Date |
|  | Sprint kickoff meeting | All members | done | 4 | 19/04 | 19/04 |
|  | Update Sprint Backlog | Sang Nguyen | done | 6 | 19/04 | 20/04 |
|  | Update Architecture Design Document | Tuan Doan | done | 7 | 20/04 | 22/04 |
|  | Update Test Plan | Thuyen Pham | done | 3 | 22/04 | 23/04 |
|  | Design Test Case for Sprint 4 | Loc Phung | done | 16 | 24/04 | 27/04 |
|  | Develop scan ticket feature | Sang Nguyen | done | 5 | 25/04 | 26/04 |
|  | Integrate advertisements in app | Sang Nguyen | done | 6 | 27/04 | 29/04 |
|  | Make messenger UI in app | Tuan Doan | done | 9 | 26/04 | 30/04 |
|  | Develop API to send and receive message in app | Loc Phung | done | 5 | 24/04 | 26/04 |
|  | Create trigger to gain social coin automation | Tuan Doan | done | 9 | 27/04 | 29/04 |
|  | Create UI for checking user wallet | Tuan Doan | done | 8 | 28/04 | 29/04 |
|  | Develop API to get list coin of user | Loc Phung | done | 7 | 26/04 | 28/04 |
|  | Enhance UI of account setting | Thuyen Pham | not done | 12 | 29/04 | 01/05 |
|  | Develop API for updating account setting | Thuyen Pham | done | 13 | 01/05 | 01/05 |
|  | User check post-interaction history | Sang Nguyen | done | 16 | 30/04 | 01/05 |
|  | Develop API for check list post-interaction history | Sang Nguyen | done | 8 | 29/04 | 01/05 |
|  | Test for Sprint 4 | Thuyen | done | 20 | 26/04 | 02/05 |
|  | Team Daily meeting | All members | done | 20 | 19/04 | 01/05 |
|  | Sprint Review meeting | All members | done | 8 | 23/04 | 23/04 |
|  | Sprint Retrospective | All members | done | 4 | 02/05 | 02/05 |
|  |  |  |  | 186 | 19/04 | 02/05 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone | 18/  04 | 19/ 04 | 20/  04 | 21/ 04 | 22/  04 | 23/ 04 | 24/  04 | 25/  04 | 26/ 04 | 27/  04 | 28/  04 | 29/  04 | 30/  04 | 01/  05 | 02/ 05 |
| Estimated Time (Hours) | 186 | 172.7 | 159.4 | 146.1 | 132.9 | 119.6 | 106.3 | 93 | 79.7 | 66.4 | 53.1 | 39.9 | 26.6 | 13.3 | 0 |
| Actual Time Remaining(Hours) | 186 | 167 | 143 | 140 | 122 | 99 | 87 | 85 | 81 | 78 | 75 | 67 | 39 | 16 | 2 |
| Actual Time(Hours) | 0 | 19 | 24 | 3 | 18 | 23 | 12 | 2 | 4 | 3 | 3 | 8 | 28 | 23 | 14 |
| Sprint kickoff meeting | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Sprint Backlog | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Architecture Design Document | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Test Plan | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Design Test Case for Sprint 4 | 0 | 0 | 2 | 1 | 4 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Develop scan ticket feature | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Integrate advertisements in app | 0 | 0 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Make messenger UI in app | 0 | 3 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Develop API to send and receive message in app | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Create trigger to gain social coin automation | 0 | 0 | 2 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Create UI for checking user wallet | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |
| Develop API to get list coin of user | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |
| Enhance UI of account setting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 1 |
| Develop API for updating account setting | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 1 | 0 | 0 | 4 | 1 | 0 |
| User check post-interaction history | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 6 | 3 |
| Develop API for check list post-interaction history | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 1 |
| Test for Sprint 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 5 | 5 |
| Team Daily meeting | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 0 |
| Sprint Review meeting | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Sprint Retrospective | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |

1. **Sprint 5**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Task | Responsible person | Status | Estimate (hours) | Start Date | End Date |
|  | Sprint kickoff meeting | All members | done | 4 | 03/05 | 03/05 |
|  | Update Sprint Backlog | Sang Nguyen | done | 8 | 03/05 | 04/05 |
|  | Update Test Plan | Thuyen Pham | done | 6 | 04/05 | 07/05 |
|  | Design Test Case for Sprint 5 | Thuyen Pham | done | 15 | 08/05 | 14/05 |
|  | Enhance UI of account setting | Tuan Doan | done | 2 | 04/05 | 07/05 |
|  | Develop API to follow other users | Sang Nguyen | done | 8 | 05/05 | 07/05 |
|  | Enhance UI for following the other users in social network | Loc Phung | done | 8 | 06/05 | 08/05 |
|  | Handle UI to recommend video in social network | Sang Nguyen | done | 11 | 08/05 | 11/05 |
|  | Develop an API to get video recommendations | Tuan Doan | done | 9 | 10/05 | 12/05 |
|  | Handle detecting video content with Google Video Intelligent Service | Thuyen Pham, Sang Nguyen | done | 19 | 06/05 | 14/05 |
|  | Remove and send notification about video including harmful contents | Sang Nguyen | done | 11 | 13/05 | 15/05 |
|  | Enhance UI to report a video | Loc Phung | done | 7 | 13/05 | 14/05 |
|  | Develop API to report a video | Tuan Doan | done | 6 | 12/05 | 13/05 |
|  | Update notifications in app | Sang Nguyen | done | 8 | 15/05 | 16/05 |
|  | Test for Sprint 5 | Loc Phung | done | 18 | 12/05 | 16/05 |
|  | Team Daily meeting | All members | done | 16 | 03/05 | 15/05 |
|  | Sprint Review meeting | All members | done | 8 | 11/05 | 11/05 |
|  | Sprint Retrospective | All members | done | 4 | 16/05 | 16/05 |
|  |  |  |  | 168 | 03/05 | 16/05 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone | 02/  05 | 03/  05 | 04/ 05 | 05/  05 | 06/ 05 | 07/  05 | 08/ 05 | 09/  05 | 10/  05 | 11/ 05 | 12/  05 | 13/  05 | 14/  05 | 15/  05 | 16/  05 |
| Estimated Time (Hours) | 168 | 156 | 144 | 132 | 120 | 108 | 96 | 84 | 72 | 60 | 48 | 36 | 24 | 12 | 0 |
| Actual Time Remaining(Hours) | 168 | 151 | 133 | 107 | 102 | 83 | 57 | 56 | 37 | 26 | 17 | 17 | 5 | 0 | 0 |
| Actual Time(Hours) | 0 | 17 | 18 | 26 | 5 | 19 | 26 | 1 | 19 | 11 | 9 | 0 | 12 | 5 | 0 |
| Sprint kickoff meeting | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Sprint Backlog | 0 | 3 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Test Plan | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Design Test Case for Sprint 5 | 0 | 2 | 5 | 5 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Enhance UI of account setting | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Develop API to follow other users | 0 | 3 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Enhance UI for following the other users in social network | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Handle UI to recommend video in social network | 0 | 0 | 4 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Develop an API to get video recommendations | 0 | 0 | 0 | 4 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Handle detecting video content with Google Video Intelligent Service | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 2 | 2 | 0 | 0 | 0 | 0 |
| Remove and send notification about video including harmful contents | 0 | 0 | 0 | 2 | 1 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 |
| Enhance UI to report a video | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |
| Develop API to report a video | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4 | 0 | 0 |
| Update notifications in app | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |
| Test for Sprint 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 3 | 1 | 4 | 0 | 4 | 1 | 0 |
| Team Daily meeting | 0 | 0 | 2 | 2 | 0 | 3 | 3 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 |
| Sprint Review meeting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |
| Sprint Retrospective | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |

1. **Sprint 6**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Task | Responsible person | Status | Estimate (hours) | Start Date | End Date |
|  | Sprint kickoff meeting | All members | done | 4 | 17/05 | 17/05 |
|  | Update Sprint Backlog | Sang Nguyen | done | 4 | 17/05 | 18/05 |
|  | Update Test Plan | Thuyen Pham | done | 4 | 17/05 | 18/05 |
|  | Design Test Case for Sprint 6 | Thuyen Pham | done | 15 | 19/05 | 22/05 |
|  | Manage all user vouchers in app | Tuan Doan | done | 9 | 18/05 | 23/05 |
|  | Develop API for managing all user vouchers | Tuan Doan | done | 11 | 23/05 | 26/05 |
|  | Transfer from social coin to voucher | Sang Nguyen | done | 9 | 19/05 | 21/05 |
|  | Develop API to manage all posts in web | Sang Nguyen | done | 8 | 20/05 | 22/05 |
|  | Manage posts in web | Loc Phung | done | 11 | 19/05 | 23/05 |
|  | Manage the list of reported posts in web | Sang Nguyen | done | 10 | 21/05 | 24/05 |
|  | Manage user coin | Tuan Doan | done | 6 | 22/05 | 25/05 |
|  | Manage user messages in web | Loc Phung | done | 7 | 26/05 | 27/05 |
|  | Update manage list of vouchers in web | Loc Phung | done | 10 | 27/05 | 29/05 |
|  | Update manage all users | Loc Phung | done | 8 | 28/05 | 29/05 |
|  | Test for Sprint 6 | Thuyen Pham | done | 16 | 26/05 | 30/05 |
|  | Team Daily meeting | All members | done | 16 | 17/05 | 29/05 |
|  | Sprint Review meeting | All members | done | 8 | 25/05 | 25/05 |
|  | Sprint Retrospective | All members | done | 4 | 30/05 | 30/05 |
|  |  |  |  | 160 | 17/05 | 30/05 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone | 16/  05 | 17/  05 | 18/ 05 | 19/  05 | 20/ 05 | 21/  05 | 22/ 05 | 23/  05 | 24/  05 | 25/ 05 | 26/  05 | 27/  05 | 28/  05 | 29/  05 | 30/  05 |
| Estimated Time (Hours) | 160 | 148.6 | 137.1 | 125.7 | 114.3 | 102.9 | 91.4 | 80 | 68.6 | 57.1 | 45.7 | 34.3 | 22.9 | 11.4 | 0 |
| Actual Time Remaining(Hours) | 160 | 153 | 128 | 112 | 98 | 74 | 47 | 46 | 27 | 15 | 7 | 7 | 5 | 0 | 0 |
| Actual Time(Hours) | 0 | 7 | 25 | 16 | 14 | 24 | 27 | 1 | 19 | 12 | 8 | 0 | 2 | 5 | 0 |
| Sprint kickoff meeting | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Sprint Backlog | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update Test Plan | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Design Test Case for Sprint 6 | 0 | 3 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Manage all user vouchers in app | 0 | 0 | 4 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |
| Develop API for managing all user vouchers | 0 | 0 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Transfer from social coin to voucher | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Develop API to manage all posts in web | 0 | 0 | 1 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Manage posts in web | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |
| Manage the list of reported posts in web | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |
| Manage user coin | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |
| Manage user messages in web | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |
| Update manage list of vouchers in web | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 2 | 0 | 0 |
| Update manage all users | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |
| Test for Sprint 6 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | 3 | 1 | 3 | 0 | 0 | 1 | 0 |
| Team Daily meeting | 0 | 0 | 3 | 2 | 2 | 2 | 3 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 |
| Sprint Review meeting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |
| Sprint Retrospective | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |